## Terraform Training Gantt
Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
FOUNDATION & BASICS
Environment Setup & Azure Account | bar: Week 1
Terraform Installation & Configuration | bar: Week 1
Azure Fundamentals Review | bar: Week 2
Terraform Core Concepts | bar: Week 2
Providers & Authentication | bar: Week 2
Variables, Types & Built-in Functions | bar: Week 2
INTERMEDIATE CONCEPTS
State Management & Remote State
Meta-arguments & Dynamic Blocks
Modules Development & Best Practices
AZURE CORE SERVICES
Virtual Machines
Storage Accounts (i.e. Blob Storage, ADLS)
Databases (SQL DB, Cosmos DB)
Container Services (ACR, AKS)
AZURE DATA SERVICES
Azure Data Factory
Azure Synapse
SQL Pools
Spark Pools
AZURE APPLICATION SERVICES
Azure App Service & Web Apps
Integration to Databases (SQL DB, Cosmos DB)
AZURE NETWORKING
Azure Load Balancer
Virtual Network
Subnets
Public IP
Network Interface
Network Security Group
Virtual Machines
Azure Traffic Manager
Integration with Web Apps
Vnet Peering
Application Gateway
Azure Firewall (routing, NAT Rules, Application Rules)
WAF
ADVANCED SERVICES & SECURITY
Security & Key Vault
Identity Management & RBAC
Monitoring & Log Analytics
ENTERPRISE PATTERNS & DEVOPS
Multi-Environment Deployment
Git Management & State Management
Azure DevOps Integration
Synapse Analytics (Optional Advanced)
Final Project & Assessment
START & END DATE | Week 1: August - November 2025

## Training Details
Week | Phase | Module | Learning Objectives | Key Activities | Deliverables
1 | Foundation | Environment Setup | Set up development environment | Azure account setup, Terraform installation | Working development environment
2 | Foundation | Core Concepts | Understand Terraform basics | HCL syntax, providers, authentication | Basic Terraform knowledge
3 | Foundation | Terraform Workflow | Master Terraform commands | init, plan, apply, destroy workflow | Terraform CLI proficiency
4 | Foundation | Variables & Functions | Dynamic configurations | Variables, types, built-in functions | Parameterized configurations
5 | Foundation | Assessment | Validate foundation knowledge | Practical exam and state introduction | Phase 1 completion
6 | Intermediate | State Management | Remote state implementation | Azure Storage backend, state locking | Remote state setup
7 | Intermediate | Meta-arguments | Advanced resource management | count, for_each, dynamic blocks | Advanced configurations
8 | Intermediate | Modules | Reusable infrastructure | Module development, versioning | Production-ready modules
9 | Intermediate | Storage Services | Azure storage solutions | Storage accounts, ADLS, blob storage | Storage infrastructure
10 | Azure Services | Compute & Networking | VM and network deployment | VMs, VNets, NSGs, load balancing | Compute infrastructure
11 | Azure Services | Advanced Services | Complex Azure services | App Services, databases, networking | End-to-end applications
12 | Advanced | Enterprise Patterns | Production deployment | Security, DevOps, final project | Enterprise-ready solution